## Working route
Blackboard Group No 02 Class NAA | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING 2B reviewed (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING 2B reviewed (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING 2B reviewed (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING 2B reviewed (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING 2B reviewed (not) DONE DONE LATE HUNG UP
reference and relative due dates |  | Update E3 to your PM class date | =====> | 2022-11-24 | Wednesday Nov.23 |  |  | PM class date plus | 9 | days |  |  | PM class date plus | 14 | days |  |  | PM class date plus | 21 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2022-12-15
Each group member | Your Project Mgmt notes on what each Process Group means to you when doing this project. | Share with team by uploading PM-Notes-myName.docx to Bb ## team channel's Files |  | Friday Nov.25 | DONE | completes their module | see Programming Comments and Programming Test Cases docs for evaluation criteria | 4 hours | see Project Milestones and Details | DONe | completes their module | see Programming Comments and Programming Test Cases docs for evaluation criteria | 4 hours | see Project Milestones and Details | DONE | completes their module | see Programming Comments and Programming Test Cases docs for evaluation criteria | 4 hours | see Project Milestones and Details | DONE
Group Meeting Agenda ==> | create MS Teams Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to group members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | Saturday Nov.26 | DONE | review progress, refine Plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. | 1 hour | Wednesday Nov.30 | DONE | Group decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status | 1 hour | Monday Dec.5 | DONE | Group decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status | 1 hour | Monday Dec.12 | DONE | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. |  | Monday Dec.12 | DID NOT DO
| request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Sunday Nov.27 | DONE | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Wednesday Nov.30 | DONE | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Monday Dec.5 | DID NOT DO | request review from professor | Request review of this file: see Project Milestones and Details page, "Request review of a file..." |  | Monday Dec.12 | DID NOT DO
Anirudh Fundamentals | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | If the notes are completed. Have they been seen by the other members to obtain feedback from. Have roles and team leader been decided? | 1 hour | Saturday Nov.26 | DONE | complete the fundamental module on time including code, comments and compiling of the module along with test cases for this module. | Fundamental module needs to be completed on time with proper commented code and compiled version. four files need to be uploaded - module.c, module.h, module-test-case.xlsx, and module-test-case.txt also the test cases needs to be included with edge cases, over the edge caes and normal case. If any of the above is not completed or it is not done properly according to the doc provided, then the work will not be accepted. | 6 hour | Thursday Dec.1 | DONE | Review professor and group feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 1 hour | Tuesday Dec.6 | DONE | Review professor and group feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 2 Hours | Tuesday Dec.13 | DONE |  |  |  | Tuesday Dec.13
Om Manipulations | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | If the notes are completed. Have they been seen by the other members to obtain feedback from. Have roles and team leader been decided? | 1 hour | Saturday Nov.26 | DONE | Review professor feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 1 hour | Thursday Dec.1 | DONE | Review professor and group feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 1 hour | Tuesday Dec.6 | DONE | Review professor and group feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 2 Hours | Tuesday Dec.13 | DONE |  |  |  | Tuesday Dec.13
Saksham Tokenizing | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | If the notes are completed. Have they been seen by the other members to obtain feedback from. Have roles and team leader been decided? | 1 hour | Saturday Nov.26 | DONE | Review professor feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 1 hour | Thursday Dec.1 | DONE | Review professor and group feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 1 hour | Tuesday Dec.6 | DONE | Review professor and group feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 2 Hours | Tuesday Dec.13 | DONE |  |  |  | Tuesday Dec.13
Justin Conversions Group Leader | Review each other's PM notes on process groups. Agree on how project will be done. Decide which module to do & choose Group Leader | If the notes are completed. Have they been seen by the other members to obtain feedback from. Have roles and team leader been decided? | 1 hour | Sunday Nov.27 | DONE | Review professor feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 1 hour | Friday Dec.2 | DONE | Review professor and group feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 1 hour | Wednesday Dec.7 | DONE | Review professor and group feedback and implement changes and fixes to plan | Peers will evaluate whether or not changes advised by the professor have been completed and met. | 2 Hours | Wednesday Dec.14 | DONE |  |  |  | Wednesday Dec.14
|  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[7 empty] | What is the group's criteria for acceptance of development (individual files) when promoted to integration (Teams group Files) -- remember the SDLC and Version Control flow? What is definition of done / good enough? Who decides that? | [11 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time 2B reviewed: status updated by team member. Other team members review and change status to DONE or back to DOING for rework. DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time 2B reviewed: status updated by team member. Other team members review and change status to DONE or back to DOING for rework. DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time 2B reviewed: status updated by team member. Other team members review and change status to DONE or back to DOING for rework. DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time 2B reviewed: status updated by team member. Other team members review and change status to DONE or back to DOING for rework. DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time 2B reviewed: status updated by team member. Other team members review and change status to DONE or back to DOING for rework. DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.